## VAR
Batch | Supplier | Task | Number of products | Completed Items | UnCategorized | Number of days | Start date | End Date | Status | Month | Worked By
GS52 | Mix batch | Categorization | 3136 | 3118 | 18 | 2 | 2016-10-01 | 2016-10-04 | Delivered | Invoiced - October- 2016 | HC Team
GS53 | Mix batch | Categorization | 12005 | 6081 | 5924 | 2 | 2016-10-05 | 2016-10-06 | Delivered | Invoiced - October- 2016 | HC Team
GS54 | Mix batch | Categorization | 47223 | 20406 | 26817 | 5 | 2016-10-07 | 2016-10-17 | Delivered | Invoiced - October- 2016 | HC Team
GS55 | Mix batch | Categorization | 26817 | 11247 | 15570 | 4 | 2016-10-18 | 2016-10-21 | Delivered | Invoiced - October- 2016 | Dr. BSW
GS56 | Mix batch | Categorization | 7487 | 6048 | 1439 | 3 | 2016-10-22 | 2016-10-26 | Delivered | Invoiced - October- 2016 | Dr. BSW
GS57 | Mix batch | Categorization | 17042 | 9126 | 7916 | 2 | 2016-10-27 | 2016-10-28 | Delivered | Invoiced - October- 2016 | Dr. BSW
GS58 | Mix batch | Categorization | 4407 | 4407 | 0 | 2 | 2016-11-02 | 2016-11-04 | Delivered | Invoiced - November- 2016 | Dr. BSW
GS59 | Mix batch | Categorization | 21618 | 11235 | 10383 | 4 | 2016-11-04 | 2016-11-09 | Delivered | Invoiced - November- 2016 | Dr. BSW
GS60 | Mix batch | Categorization | 10382 | 5022 | 5360 | 2 | 2016-11-10 | 2016-11-11 | Delivered | Invoiced - November- 2016 | Dr. BSW
GS61 | Eclass mapping Johnson and Johnson | Eclass | 86578 | 15572 | 71006 | 3 | 2016-11-12 | 2016-11-16 | Delivered | Invoiced - November- 2016 | Dr. BSW
GS62 | Eclass mapping Johnson and Johnson | Eclass | 71006 | 16832 | 54174 | 3 | 2016-11-17 | 2016-11-21 | Delivered | Invoiced - November- 2016 | Dr. BSW
GS63 | Eclass mapping Johnson and Johnson | Eclass | 54174 | 10046 | 44128 | 3 | 2016-11-22 | 2016-11-24 | Delivered | Invoiced - November- 2016 | Dr. BSW
GS64_B1 | Stone computers | Categorization | 4516 | 4514 | 2 | 2 | 2016-11-25 | 2016-11-28 | Delivered | Invoiced - November- 2016 | Dr. BSW
GS64_B2 | Thermofisher | Categorization | 18916 | 18037 | 879 |  | 2016-11-25 | 2016-11-28 |  | Invoiced - November- 2016 | Dr. BSW
GS65 | Eclass mapping Johnson and Johnson | Eclass | 44128 | 4251 | 39877 | 1 | 2016-11-29 | 2016-11-30 | Delivered | Invoiced - November- 2016 | Dr. BSW
GS66 | Eclass mapping Smith and Nephew | Eclass | 28794 | 15805 | 12989 | 3 | 2016-11-30 | 2016-12-02 | Delivered | Invoiced - December- 2016 | Dr. BSW
GS67 | Eclass mapping Smith and Nephew | Eclass | 12989 | 12989 | 0 | 3 | 2016-12-05 | 2016-12-07 | Delivered | Invoiced - December- 2016 | Dr. BSW
GS68 | Categorization - Mix batch | Categorization | 18140 | 10066 | 8074 | 3 | 2016-12-08 | 2016-12-12 | Delivered | Invoiced - December- 2016 | Dr. BSW
GS69 | Categorization - VWR_Fisher | Categorization | 5134 | 2703 | 2431 | 2 | 2016-12-13 | 2016-12-14 | Delivered | Invoiced - December- 2016 | Dr. BSW
GS70 | Eclass mapping Johnson and Johnson | Eclass | 27388 | 13167 | 14221 | 4 | 2016-12-15 | 2016-12-20 | Delivered | Invoiced - December- 2016 | HC Team
GS71 | Eclass mapping Johnson and Johnson | Eclass | 14221 | 14221 | 0 | 4 | 2016-12-20 | 2016-12-26 | Delivered | Invoiced - December- 2016 | HC Team
GS72 | Cleansing | Cleansing | 12591 | 12591 | 0 | 5 | 2016-12-20 | 2016-12-30 | Delivered | Invoiced - December- 2016 | HC Team
GS73 | Categorization - Mix batch | Categorization | 2513 | 2372 | 141 | 1 | 2017-01-02 | 2017-01-04 | Delivered | Invoiced - January - 2017 | Dr. BSW
GS74 | Laboratory Equipment Spares and Accessories items | Categorization | 46783 | 34577 | 12206 | 5 | 2017-01-04 | 2017-01-16 | Delivered | Invoiced - January - 2017 | HC Team
GS75 | Top10 | Categorization | 1926 | 1919 | 7 | 2 | 2017-01-06 | 2017-01-09 | Delivered | Invoiced - January - 2017 | Dr. BSW
GS76 | Categorization - Mix batch | Categorization | 148 | 142 | 6 | 1 | 2017-01-10 | 2017-01-10 | Delivered | Invoiced - January - 2017 | HC Team
GS77 | New Batch and Task | Multi | 1015 | 1015 | 0 | 2 | 2017-01-11 | 2017-01-12 | Delivered | Invoiced - January - 2017 | HC Team
GS78 | Categorization - Mix batch | Categorization | 1454 | 1454 | 0 | 2 | 2017-01-16 | 2017-01-17 | Delivered | Invoiced - January - 2017 | Dr. BSW
GS79 | Categorization - Review | Categorization | 2369 | 2369 | 0 | 2 | 2017-01-18 | 2017-01-19 | Delivered | Invoiced - January - 2017 | HC Team
GS80 | Categorization - Mix batch | Categorization | 1553 | 1552 | 1 | 2 | 2017-01-20 | 2017-01-23 | Delivered | Invoiced - January - 2017 | HC Team
GS81 | Categorization - Mix batch | Categorization | 6338 | 5536 | 802 | 3 | 2017-01-24 | 2017-01-27 | Delivered | Invoiced - January - 2017 | 5940- Dr BSW/398 HC Team
GS82 | Categorization - Mix batch | Categorization | 1497 | 1490 | 7 | 2 | 2017-01-30 | 2017-01-31 | Delivered | Invoiced - January - 2017 | HC Team
GS83 | Smith and Nephew missing descriptions | Description updation | 160 | 160 | 0 | 1 | 2017-02-01 | 2017-02-01 | Delivered | Invoiced - February - 2017 | HC Team
GS81 | Categorization - Mix batch | Categorization | 802 | 795 | 7 | 1 | 2017-02-02 | 2017-02-02 | Delivered | Invoiced - February - 2017 | Dr. BSW
GS84 | Categorization - Mix batch | Categorization | 1171 | 1171 | 0 | 1 | 2017-02-05 | 2017-02-05 | Delivered | Invoiced - February - 2017 | 906- Dr BSW/265 HC Team
GS85_B1 | ZimmerBiomet | Description updation | 91038 | 9869 | 0 | 3 | 2017-02-07 | 2017-02-09 | Delivered | Invoiced - February - 2017 | HC Team
GS85_B2 | ZimmerBiomet | Description updation |  | 16366 | 0 | 5 | 2017-02-10 | 2017-02-16 | Delivered | Invoiced - February - 2017 | HC Team
GS85_B3 | ZimmerBiomet | Description updation |  | 64713 | 0 | 16 | 2017-02-07 | 2017-02-28 | Delivered | Invoiced - February - 2017 | HC Team
GS86_B2 | Codex | Categorization | 2913 | 2913 | 0 | 2 | 2017-02-28 | 2017-03-02 | Delivered | Invoiced - March- 2017 | MRO Team
GS87 | XMA Items | Categorization | 1241 | 1241 | 0 | 2 | 2017-03-02 | 2017-03-03 | Delivered | Invoiced - March- 2017 | MRO Team
GS88 | Miltenyi Biotec | Categorization | 1294 | 1294 | 0 | 1 | 2017-03-06 | 2017-03-06 | Delivered | Invoiced - March- 2017 | Dr. BSW
GS89 | Cambridge Bio | Categorization | 70483 |  |  |  | 2017-03-07 | ASAP | On HOLD/ file completed | Invoiced - March- 2017 | Dr. BSW
GS90 | Categorization - Mix batch | Categorization | 1150 | 1150 | 0 | 1 | 2017-03-07 | 2017-03-07 | Delivered | Invoiced - March- 2017 | HC Team
GS91 | Synthes | Centralisation | 61817 | 61817 | 0 |  | 2017-03-09 | 2017-03-16 | Delivered | Invoiced - March- 2017 | HC Team
GS92 | RS Components | Categorization | 254990 | 253568 | 1422 | 14 | 2017-03-17 | 2017-04-05 | Delivered | Invoiced - March- 2017 | MRO Team
GS93 | OffCatItems_SearchBetterData | Cleansing | 994 | 86 | 908 | 1 | 2017-04-06 | 2017-04-06 | Delivered | Invoiced - April- 2017 | GS-92 Records – 34646 for April
GS94 | Boston | Centralisation | 11122 | 11122 | 0 | 3 | 2017-04-10 | 2017-04-12 | Delivered | Invoiced - April- 2017 | HC Team
GS95 | Sigma | Categorization | 42230 | 42230 | 0 | 5 | 2017-04-13 | 2017-04-19 | Delivered | Invoiced - April- 2017 | Dr. BSW
GS96 | - | - | - | - | - | - | - | - | - | Invoiced - April- 2017 | No File for GS96
GS97 | Mix Vendor | Categorization | 949 | 949 | 0 | 2 | 2017-04-20 | 2017-04-21 | Delivered | Invoiced - April- 2017 | MRO Team
GS98 | Office Depot mappings | Categorization | 6465 | 6296 | 169 | 3 | 2017-04-24 | 2017-04-25 | Delivered | Invoiced - April- 2017 | 5204- Dr BSW/1261 MRO Team
GS99 | Mix Vendor | Categorization | 1951 | 1949 | 2 | 2 | 2017-04-26 | 2017-04-27 | Delivered | Invoiced - April- 2017 | 1802- Dr BSW/149 MRO Team
GS100 | Consturction suppliers | Categorization | 1071 | 1067 | 4 | 2 | 2017-04-28 | 2017-05-02 | Delivered | Invoiced - May- 2017 | MRO Team
GS101 | Medtronic | Cleansing | 34347 | 34347 | 0 | 4 | 2017-05-03 | 2017-05-08 | Delivered | Invoiced - May- 2017 | HC Team
GS102 | Mix Vendor | Categorization | 14351 | 14351 | 0 | 2 | 2017-05-05 | 2017-05-10 | Delivered | Invoiced - May- 2017 | Dr. BSW
GS103 | Categorization - VWR | Categorization | 52360 | 52358 | 2 | 5 | 2017-05-11 | 2017-05-31 | Delivered | Invoiced - May- 2017 | 51166-Dr BSW/ 1197-HC Team
GS104 | Davies and Chadwicks | Categorization | 2390 | 2385 | 5 | 3 | 2017-06-01 | 2017-06-05 | Delivered | Invoiced - June- 2017 | MRO Team
GS105 | Thorlabs | Categorization | 4956 | 4956 | 0 | 2 | 2017-06-06 | 2017-06-07 | Delivered | Invoiced - June- 2017 | Dr. BSW
GS106 | FisherScientific | Categorization | 24806 | 24777 | 29 | 7 | 2017-06-07 | 2017-06-15 | Delivered | Invoiced - June- 2017 | 24071- Dr BSW/735 MRO Team
GS107 | Mixed | Categorization | 4098 | 4095 | 3 | 2 | 2017-06-16 | 2017-06-19 | Delivered | Invoiced - June- 2017 | 2758- Dr BSW/1340 MRO Team
GS108 | Mixed | Categorization | 8247 | 8188 | 59 | 3 | 2017-06-20 | 2017-06-22 | Delivered | Invoiced - June- 2017 | 2016- Dr BSW/6231 MRO Team
GS109 | Merck | Eclass | 30417 | 6416 | 24001 | 1.5 | 2017-06-23 | 2017-06-26 | Delivered | Invoiced - June- 2017 | Dr. BSW
GS110 | Mixed | Eclass | 6084 | 5878 | 206 | 2.5 | 2017-06-26 | 2017-06-28 | Delivered | Invoiced - June- 2017 | 1370- Dr BSW/4714 MRO Team
GS111 | Mixed | Categorization | 890 | 888 | 2 | 1 | 2017-06-29 | 2017-06-30 | Delivered | Invoiced - June- 2017 | MRO Team
GS112 | FisherScientific | Categorization | 32291 | 24489 | 0 | 5 | 2017-07-03 | 2017-07-07 | Delivered | Invoiced - July- 2017 | 17814-Dr BSW/ 6665-HC Team
|  |  |  | 7802 | 0 | 3 | 2017-07-12 | 2017-07-17 | Delivered | Invoiced - July- 2017 | 7802 - Dr BSW
GS113 | Generon SW-198739 | Eclass | 198739 | 52395 |  | 10 | 2018-05-07 | 2018-06-04 | Delivered | Invoiced - June- 2018 | Dr. BSW
|  |  |  | 51303 |  | 10 | 2018-06-05 | 2018-06-26 | Delivered | Invoiced - June- 2018
|  |  |  | 30030 |  | 7 | 2018-06-27 | 2018-07-05 | Delivered | Invoiced - July- 2018
|  |  |  | 32101 |  | 7 | 2018-07-06 | 2018-07-24 | Delivered | Invoiced - July- 2018
|  |  |  | 32910 |  | 7 | 2018-07-25 | 2018-08-02 | Delivered | Invoiced - August- 2018
| Generon SW2-280378 |  | 280378 | 61416 |  | 19 | 2017-07-10 | 2017-11-29 | Delivered | Invoiced - November- 2017
|  |  |  | 18697 |  | 5 | 2017-11-30 | 2017-12-07 | Delivered | Invoiced - December- 2017
|  |  |  | 22912 |  | 7 | 2017-12-29 | 2018-01-08 | Delivered | Invoiced - January - 2018
|  |  |  | 19226 |  | 5 | 2018-01-09 | 2018-01-16 | Delivered | Invoiced - January - 2018
|  |  |  | 13396 |  | 3 | 2018-01-17 | 2018-01-19 | Delivered | Invoiced - January - 2018
|  |  |  | 15206 |  | 4 | 2018-01-25 | 2018-01-31 | Delivered | Invoiced - January - 2018
|  |  |  | 16006 |  | 4 | 2018-02-15 | 2018-02-20 | Delivered | Invoiced - February - 2018
|  |  |  | 21296 |  | 6 | 2018-02-21 | 2018-02-28 | Delivered | Invoiced - February - 2018
|  |  |  | 31143 |  | 9 | 2018-03-01 | 2018-03-27 | Delivered | Invoiced - March- 2018
|  |  |  | 33450 |  | 6 | 2018-04-06 | 2018-04-16 | Delivered | Invoiced - April- 2018
|  |  |  | 27630 |  | 5 | 2018-04-25 | 2018-05-07 | Delivered | Invoiced - May- 2018
GS114 | Mixed | Categorization | 78584 | 41193 | 18 | 5 | 2017-07-19 | 2017-07-25 | Delivered | Invoiced - July- 2017 | Dr. BSW
|  |  |  | 37373 |  | 7 | 2017-07-26 | 2017-08-03 | Delivered | Invoiced - August- 2017
GS115 | Mixed | Categorization | 276 | 276 | 0 | 1 | 2017-07-19 | 2017-07-19 | Delivered | Invoiced - July- 2017 | MRO Team
GS116 | Mixed | Categorization | 7852 | 7852 | 0 | 2 | 2017-08-04 | 2017-08-07 | Delivered | Invoiced - August- 2017 | Dr. BSW
GS117 | Mixed | Categorization | 83240 | 20727 | 0 | 5 | 2017-08-10 | 2017-08-18 | Delivered | Invoiced - August- 2017 | Dr. BSW -45571/MRO Team -37669
|  |  |  | 22095 | 0 | 5 | 2017-08-18 | 2017-08-24 | Delivered | Invoiced - August- 2017
|  |  |  | 12362 | 0 | 3 | 2017-08-29 | 2017-08-31 | Delivered | Invoiced - August- 2017
|  |  |  | 18880 | 0 | 8 | 2017-09-01 | 2017-09-13 | Delivered | Invoiced - September- 2017
|  |  |  | 9176 | 0 | 4.5 | 2017-09-14 | 2017-09-25 | Delivered | Invoiced - September- 2017
GS118 | Laboratory Equipment Spares and Accessories items | Categorization | 2175 | 2175 | 0 | 1.5 | 2017-08-24 | 2017-08-28 | Delivered | Invoiced - August- 2017 | Dr. BSW
GS119 | Mixed | Categorization | 4361 | 4361 | 0 | 1 | 2017-09-20 | 2017-09-21 | Delivered | Invoiced - September- 2017 | Dr. BSW
GS120 | Mixed | Categorization | 5435 | 5413 | 22 | 1 | 2017-09-19 | 2017-09-20 | Delivered | Invoiced - September- 2017 | Dr. BSW
GS121 | Mixed | Categorization | 4123 | 4084 | 39 | 1 | 2017-09-26 | 2017-09-26 | Delivered | Invoiced - September- 2017 | Dr. BSW
GS122 | Mixed | Categorization | 86977 | 56735 | 0 | 8 | 2017-09-27 | 2017-10-10 | Delivered | Invoiced - October- 2017 | MRO Team/HC/BSW
|  |  |  | 27324 | 0 | 8 | 2017-10-12 | 2017-10-24 | Delivered | Invoiced - October- 2017
|  |  |  | 2918 | 0 | 3 | 2017-10-25 | 2017-10-27 | Delivered | Invoiced - October- 2017
GS123 | Laboratory Equipment Spares and Accessories items | Categorization | 3895 | 3895 | 0 | 1 | 2017-10-11 | 2017-10-11 | Delivered | Invoiced - October- 2017 | Dr. BSW
GS124 | Laboratory Equipment Spares and Accessories items | Categorization | 3192 | 3189 | 3 | 1 | 2017-10-30 | 2017-10-30 | Delivered | Invoiced - October- 2017 | Dr. BSW
GS125 | Laboratory Equipment Spares and Accessories items | Categorization | 2174 | 2174 | 0 | 1 | 2017-10-31 | 2017-10-31 | Delivered | Invoiced - October- 2017 | Dr. BSW
GS126 | Laboratory Equipment Spares and Accessories items | Categorization | 80847 | 38991 | 22 | 5.5 | 2017-11-06 | 2017-11-13 | Delivered | Invoiced - November- 2017 | Dr. BSW
|  |  |  | 41834 |  | 6 | 2017-11-14 | 2017-11-22 | Delivered | Invoiced - November- 2017
GS127 | Laboratory Equipment Spares and Accessories items | Categorization | 7914 | 6371 | 1232 | 2 | 2017-11-02 | 2017-11-03 | Delivered | Invoiced - November- 2017 | MRO Team/HC/BSW
|  |  |  | 311 |  | 0.5 | 2017-11-06 | 2017-11-06 | Delivered | Invoiced - November- 2017
GS128 | Laboratory Equipment Spares and Accessories items | Categorization | 21535 | 21535 | 0 | 3 | 2017-11-23 | 2017-11-27 | Delivered | Invoiced - November- 2017 | Dr. BSW
GS129 | Mixed | Categorization | 33238 | 18471 | 0 | 5 | 2017-12-07 | 2017-12-13 | Delivered | Invoiced - December- 2017 | Dr. BSW
|  |  |  | 10129 | 0 | 7 | 2017-12-14 | 2017-12-22 | Delivered | Invoiced - December- 2017 | Dr. BSW
|  |  |  | 4638 | 0 | 3 | 2017-12-26 | 2017-12-28 | Delivered | Invoiced - December- 2017 | Dr. BSW
GS130 | Mixed | Categorization | 6164 | 6060 | 104 | 2 | 2018-01-23 | 2018-01-24 | Delivered | Invoiced - January - 2018 | HC/BSW
GS131 | Mixed | Categorization | 9399 | 9399 | 0 | 3 | 2018-02-02 | 2018-02-06 | Delivered | Invoiced - February - 2018 | BSW
GS132 | Mixed | Categorization | 8888 | 8716 | 172 | 3 | 2018-02-06 | 2018-02-09 | Delivered | Invoiced - February - 2018 | HC/BSW -5247
GS133 | Mixed | Categorization/Eclass | 7316 | 7316 | 0 | 2 | 2018-02-12 | 2018-02-14 | Delivered | Invoiced - February - 2018 | BSW
GS134 | Mixed | Categorization | 8146 | 5495 | 0 | 2 | 2018-03-06 | 2018-03-07 | Delivered | Invoiced - March- 2018 | BSW
|  |  |  | 2651 |  | 2 | 2018-03-12 | 2018-03-14 | Delivered | Invoiced - March- 2018 | BSW
GS135 | Mixed | Categorization | 4906 | 2558 | 16 | 2 | 2018-03-14 | 2018-03-16 | Delivered | Invoiced - March- 2018 | BSW
|  |  |  | 2332 |  | 2 | 2018-03-19 | 2018-03-20 | Delivered | Invoiced - March- 2018 | BSW
GS136 | Mixed | Categorization | 1829 | 1828 | 1 | 1 | 2018-03-22 | 2018-03-22 | Delivered | Invoiced - March- 2018 | MRO Team-1819/BSW-510
GS137 | Mixed | Categorization | 21851 | 21851 | 0 | 6 | 2018-03-28 | 2018-04-06 | Delivered | Invoiced - April- 2018 | BSW
GS138 | Mixed | Categorization | 1926 | 1924 | 2 | 1 | 2018-04-06 | 2018-04-09 | Delivered | Invoiced - April- 2018 | BSW
GS139 | Mixed | Categorization | 20644 | 20579 | 65 | 6 | 2018-04-17 | 2018-04-24 | Delivered | Invoiced - April- 2018 | BSW
GS140 | Mixed | Categorization | 10000 | 10000 | 0 | 2 | 2018-05-02 | 2018-05-04 | Delivered | Invoiced - May- 2018 | BSW
GS141 | Mixed | Categorization | 4016 | 3955 | 61 | 2 | 2018-05-08 | 2018-05-10 | Delivered | Invoiced - May- 2018 | BSW-3663/MRO-1732/353
GS142 | Mixed | Categorization | 1481 | 1406 | 75 | 2 | 2018-05-18 | 2018-05-21 | Delivered | Invoiced - May- 2018 | MRO
GS143 | Mixed | Categorization | 7741 | 7731 | 10 | 7 | 2018-05-21 | 2018-05-31 | Delivered | Invoiced - May- 2018 | BSW-6971/MRO-11795
|  |  | 11205 | 11168 | 37
GS144 | Mixed | Categorization | 15411 | 11028 | 84 | 4 | 2018-06-12 | 2018-06-15 | Delivered | Invoiced - June- 2018 | BSW
|  |  |  | 4299 | 0 | 1 | 2018-06-18 | 2018-06-18 | Delivered | Invoiced - June- 2018 | BSW
GS145 | Mixed | Categorization | 7874 | 7244 | 4 | 2 | 2018-07-13 | 2018-07-19 | Delivered | Invoiced - July- 2018 | BSW
|  |  |  | 626 | 0 | 2 | 2018-07-20 | 2018-07-20 | Delivered | Invoiced - July- 2018 | BSW
GS146 | Mixed | Categorization | 514445 | 35517 | 0 | 11 | 2018-08-03 | 2018-08-31 | Delivered | Invoiced - August- 2018 | BSW | Aug - 3,14,16,17,20,24,27,28,29,30,31
|  |  |  | 49848 | 0 | 16 | 2018-09-02 | 2018-10-26 | Delivered | Invoiced - October- 2018 | BSW | Sep -2,3,4,5,6,7,11, Oct-15-26
[7 empty] | Oct.. 29, 30 Nov 7 |  |  | For Dec | BSW
[10 empty] | For Dec | BSW
|  |  |  | 429080 | [5 empty] | For Dec | BSW
GS147 | Mixed | Categorization | 5658 | 5653 | 5 | 3 | 2018-08-06 | 2018-08-08 | Delivered | Invoiced - August- 2018 | BSW
|  |  | 3836 | 3826 | 10 | 3 | 2018-08-06 | 2018-08-13 | Delivered | Invoiced - August- 2018 | BSW
GS148 | Mixed | Categorization | 6950 | 6889 | 61 | 3 | 2018-08-21 | 2018-08-23 | Delivered | Invoiced - August- 2018 | BSW
GS149 | Mixed | Categorization | 1479 | 1468 | 11 | 3 | 2018-09-12 | 2018-09-15 | Delivered | Invoiced - September- 2018 | BSW
|  |  | 75026 | 40972 | 0 | 10 | 2018-09-17 | 2018-09-28 | Delivered | Invoiced - September- 2018 | BSW | 2018-09-21
|  |  |  | 33993 | 61 | 9 | 2018-10-01 | 2018-10-12 | Delivered | Invoiced - October- 2018 | BSW | 2018-10-06
GS150 | Mixed | Categorization | 774 | 761 | 13 | 1 | 2018-09-27 | 2018-09-27 | Delivered | Invoiced - September- 2018 | BSW
GS151 | Mixed | Categorization | 8505 | 8505 | 0 | 4 | 2018-10-31 | 2018-11-06 | Delivered | Invoiced - November- 2018 | BSW
GS152 | Mixed | Categorization | 5348 | 5338 | 10 | 6 | 2018-11-09 | 2018-11-16 | Delivered | Invoiced - November- 2018 | BSW
|  |  | 10992 | 10986 | 6 | 8 | 2018-11-19 | 2018-11-28 | Delivered | Invoiced - November- 2018 | BSW
GS153 | Mixed | Categorization | 15959 | 15934 | 25 | 7 | 2018-11-29 | 2018-12-07 | Delivered | For Dec | BSW
GS154 | Mixed | Eclass + GTIN | 56321 |  |  |  | 2018-12-10 |  |  | For Dec | BSW

## GS146 Track
Batch | Supplier | Task | Number of products | Completed Items | Pending | Number of days | Start date | End Date | Status | Month | Worked By
GS113 | Generon SW1-198739 | Eclass | 479117 |  |  |  | 2017-07-10 | 2017-09-08 | WIP |  | Dr. BSW
Generon SW2-280378
GS113 | Generon SW2-280378 | Mapping and eCl@ss | 280378 |  |  | 2 | 2017-07-10 | 2017-07-11 | WIP |  | Dr. BSW
GS113 | Generon SW2-280378 | Mapping and eCl@ss | 280378 |  |  | 2 | 2017-07-17 | 2017-07-18 | WIP |  | Dr. BSW
GS113 | Generon SW2-280378 | Mapping and eCl@ss | 280378 |  |  | 2.5 | 2017-08-08 | 2017-08-10 | WIP |  | Dr. BSW
GS113 | Generon SW2-280378 | Mapping and eCl@ss | 280378 |  |  | 7 | 2017-09-25 | 2017-10-03 | WIP |  | Dr. BSW
GS113 | Generon SW2-280378 | Mapping and eCl@ss | 280378 |  |  | 6 | 2017-10-24 | 2017-10-29 | Completed |  | Dr. BSW
GS113 | Generon SW1-198739 | Mapping and eCl@ss | 198739 |  |  | 1 | 2017-10-30 | 2017-10-30 | WIP |  | Dr. BSW
GS113 | Generon SW1-198739 | Mapping and eCl@ss | 198739 |  |  |  | 2017-11-27 |  | WIP |  | Dr. BSW
GS149 | Mixed | Categorization | 75026 | 40972 | 34054 | 5 | 2018-09-17 | 2018-09-21
|  |  |  | 34054 | 0 | 6 | 2018-10-01 | 2018-10-06
GS146 | Mixed | Categorization | 514445 | 65000 | 449445 | 19 | 2018-07-26 | 26,27,30,31,1,2,3,13,14,16,17,20,23,24, 27, 28,29,30,31 | wip |  | Dr. BSW
|  |  |  | 33254 | 416191 |  |  | 2,3,4,5,6,7,11,12
|  |  |  | 16594 |  |  |  | 8,9,10,11,12,15-20
|  |  | 514445 | 35517
29483
|  |  |  | 29483 | On Hand

## Sheet2
Batch | Supplier | Task | Number of products | Completed Items | Number of days | Start date | End Date
GS112 | FisherScientific | Categorization | 32291 | 24489 | 5 | 2017-07-03 | 2017-07-07
|  |  |  | 7802 | 3 | 2017-07-12 | 2017-07-17
GS114 | Mixed | Categorization | 78584 | 41193 | 5 | 2017-07-19 | 2017-07-25
GS115 | Mixed | Categorization | 276 | 276 | 1 | 2017-07-19 | 2017-07-19
Batch | Supplier | Task | Number of | Completed | Number | Received Date | Delivered Date
|  |  | products | Items | of days
GS104 | Davies and Chadwicks | Categorization | 2390 | 2385 | 3 | 2017-06-01 | 2017-06-05
GS105 | Thorlabs | Categorization | 4956 | 4956 | 2 | 2017-06-06 | 2017-06-07
GS106 | FisherScientific | Categorization | 24806 | 24777 | 7 | 2017-06-07 | 2017-06-15
GS107 | Mixed | Categorization | 4098 | 4095 | 2 | 2017-06-16 | 2017-06-19
GS108 | Mixed | Categorization | 8247 | 8188 | 3 | 2017-06-20 | 2017-06-22
GS109 | Merck | Eclass | 30417 | 6416 | 1.5 | 2017-06-23 | 2017-06-26
GS110 | Mixed | Eclass | 6084 | 5878 | 2.5 | 2017-06-26 | 2017-06-28
GS111 | Mixed | Categorization | 890 | 888 | 1 | 2017-06-29 | 2017-06-30
Batch | Supplier | Task | Number of | Completed | Number | Received Date | Delivered Date
|  |  | products | Items | of days
GS114 | Mixed | Categorization | 78584 | 37373 | 7 | 2017-07-26 | 2017-08-03
GS116 | Mixed | Categorization | 7852 | 7852 | 2 | 2017-08-04 | 2017-08-07
GS118 | Laboratory Equipment Spares and Accessories items | Categorization | 2175 | 2175 | 1.5 | 2017-08-24 | 2017-08-28
2018-08-01
Batch | Supplier | Task | Number of | Completed | Number | Received Date | Delivered Date
|  |  | products | Items | of days
GS113- SW2 – Priority1 | Mixed | E-Class | 479117 | B5 - 32910 | 7 | 2018-07-25 | 2018-08-02
GS112 | FisherScientific | Categorization | 5658 | 5653 | 3 | 2018-08-06 | 2018-08-08
|  |  | 3836 |  | 3 | 2018-08-06 | 2018-08-09
Aug-2018 VAR Details:
Batch | Supplier | Task | Number of | Completed | Number | Received Date | Delivered Date
|  |  | products | Items | of days
GS-149 | Mixed | Categorization | 1479 | 1479 | 3 | 2018-09-12 | 2018-09-15
| Mixed | Categorization | 75026 | B1-40972 | 10 | 2018-09-17 | 2018-09-28
GS-150 | Mixed | Categorization | 774 | 761 | 1 | 2018-08-26 | 2018-09-27
Note:
1. Below is the pending/remaining status of the Batch on hand:
Batch | File | Number of products | Delivered | Pending | Remarks
GS146 | Mixed | 514445 | 35517 | 478928 | Work in Progress